## Sheet1
# | Task | Start | Effort | 2022-04-06 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | 2022-05-11 | 2022-05-18 | 2022-05-25 | 2022-06-01 | 2022-06-08 | 2022-06-15 | 2022-06-22
1 | Timesheet | 2022-04-06 | 16h
2 | Timesheet Management | 2022-04-20 | 16h
3 | Timesheet Data verification and testing | 2022-05-04 | 8h
4 | Labour Reports | 2022-05-11 | 16h
5 | Labour Report verification and testing | 2022-05-25 | 8h
6 | Previous Timesheets Report | 2022-06-01 | 8h
7 | Previous Timesheets verification and testing | 2022-06-08 | 8h
8 | Final testing and deployment | 2022-06-15 | 16h
# | Task | Start | Effort | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19
1 | Raise job | 2022-06-20 | 4h
2 | Strip report | 2022-06-20 | 12h
3 | Workscope /Estimation | 2022-07-04 | 8h
4 | Formal quote | 2022-07-11 | 8h
5 | Process to date + email quote to user | 2022-07-18 | 8h
6 | Work instructions and requisitions | 2022-07-25 | 8h
7 | Work on Job | 2022-08-01 | 8h
8 | Process to date + alert workshop about job | 2022-08-08 | 8h
9 | Pre-Assembly/Assembly | 2022-08-15 | 8h
11 | Paint/QA/Testing | 2022-08-22 | 8h
12 | Process to date + alert about finished job | 2022-08-29 | 8h
13 | End-to-end testing and deployment | 2022-09-05 | 24h