## Question 1
Most students classify the projects as follows:
Compliance: d., g., i.
Operational: a., c., j.
Strategic: b., e., f., h.
Most students claim it was not too difficult to classify the projects other than they had to make judgment calls given the limited information.
In real life they would have such information. Debates occur around whether converting the heating system to solar polar was an operational necessity or to fit the eco-friendly image.
Likewise, launching the promotional campaign with Hawaii Airlines would be considered strategic if it promoted the eco-tourism theme, otherwise it could be consider operational.
Follow Up Question - What do you think you now know that would be useful for managing projects at the hotel?
By classifying the projects, prioritizing is more easily done. Different selection criteria can be used for selecting strategic versus operational projects.
Financially, senior management would have more information to divide the total money pie allocated to projects.
Click on the tabs below to see solutions to the different questions:

## Question 2a
Instruction: Fill in the following template to answer question 2a
| Discounted rate | 0.2
| Project | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | TOTAL | Discount Factor = 1/(1+discountRate)^year
| Investment/Cost | 0.2 Year 0: -50000
| Discount factor | 1 | 0.83333 | 0.69444 | 0.5787 | 0.48225 | 0.40188
| Discounted costs | -50000 | 0 | 0 | 0 | 0 | 0 | 50000
PLEASE SCROLL DOWN TO FIND SIMPLER TEMPLATE
| Cash Inflows/Benefits | 0 | 15000 | 25000 | 30000 | 20000 | 15000
| Discount factor | 1 | 0.83333 | 0.69 | 0.58 | 0.48 | 0.4
| Discounted benefits | 0 | 12500 | 17361.1111 | 17361.1111 | 9645.0617 | 6028.1636 | 62895.4475
| Discounted Benefits - costs | 50000 | 12500 | 17361.1111 | 17361.1111 | 9645.0617 | 6028.1636 | 12895.4475
| Cumulative Benefits - costs | -50000 | -37500 | -20138.8889 | -2777.7778 | 6867.284 | 12895.4475
| NPV | 0.2 Year 0: 12895.45; 0.2 Year 1: 62895.45-50000
| ROI | 0.2 Year 0: 25.79%; 0.2 Year 1: 12,895.45/50000; 0.2 Year 4: *Compute Payback:
|  | 0.2 Year 4: Between years 3 and 4. |  | Formula = 365*(Y1/(Y2+Y1))
| Compute using Excel NPV Function | 0.2 Year 4: ??days = 365*(2777.78/(6867.284+2777.78)) |  | 105.1201
| NPV | 0.2 Year 0: 12895.4475; 0.2 Year 4: =; 0.2 Year 5: 105.1201
[6 empty] | = | day 105 in Year 4
Simpler Template
|  | Discount rate | 0.2
| Year | 0 | 1 | 2 | 3 | 4 | 5
Inflows
| Outflows | Discount rate 0: 50000
| Netflows | -50000 | 15000 | 25000 | 30000 | 20000 | 15000 |  | PV = FV / (1+r)^n |  | DF = Discount factor
| Discount factor (from Discount factor table) | 1 | 0.83333 | 0.69444 | 0.5787 | 0.48225 | 0.40188 |  | = FV * 1/(1+r)^n
[9 empty] | = FV * DF |  | Discount rate is sometimes called rate of return.
| PV of netflows | -50000 | 12500 | 17361.1111 | 17361.1111 | 9645.0617 | 6028.1636
| PV of netflows (using formula) | -50000 | 12500 | 17361.1111 | 17361.1111 | 9645.0617 | 6028.1636 |  | Discount rate and discount factor are not same thing.
| NPV | Discount rate 0: 12895.4475
| NPV using excel function | Discount rate 0: 12895.4475

## Question 2b
Instruction: Fill in the following template to answer question 2b
2b. If the required rate of return is 20 per cent, conduct a discounted cash flow calculation to determine the NPV
Just change the discount rate = 0.23 (23%) and then change/recalculate the Discount Factors for 0.23. (20% Rate of return + 3% inflation)
|  | 0.23 | (Discount Rate)
| Project | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | TOTAL | Discount Factor = 1/(1+discountRate)^year
| Investment/Cost | 50000 | 0 | 0 | 0 | 0 | 0
| Discount factor | 1 | 0.81301 | 0.66098 | 0.53738 | 0.4369 | 0.3552
| Discounted costs | 50000 | 0 | 0 | 0 | 0 | 0 | 50000
| Cash Inflows/Benefits | 0 | 15000 | 25000 | 30000 | 20000 | 15000
| Discount factor | 1 | 0.81301 | 0.66098 | 0.53738 | 0.4369 | 0.3552
| Discounted benefits | 0 | 12195.122 | 16524.5555 | 16121.5176 | 8737.9499 | 5328.0182 | 58907.1631
| Discounted Benefits - costs | -50000 | 12195.122 | 16524.5555 | 16121.5176 | 8737.9499 | 5328.0182 | 8907.1631
| Cumulative Benefits - costs | -50000 | -37804.878 | -21280.3226 | -5158.805 | 3579.1449 | 8907.1631
| NPV | 0.23 Year 0: 8907.1631; (Discount Rate) Year 1: Disc benefit minus disc cost
| ROI | 0.23 Year 0: 17.81%; (Discount Rate) Year 4: *Compute Payback:
Look at the (Cumulative disc. Benefits - Costs), it starts generate positive amount in year 4,
| Compute using Excel NPV Function | (Discount Rate) Year 4: this shows that the project has payback somewhere between year 3 and year 4.
| NPV | 0.23 Year 0: 8907.1631; (Discount Rate) Year 4: 3 years and ?? Days
??days = 365*(2777.78/(6867.284+2777.78))
[6 empty] | = | 215.4928
[6 empty] | = | day 216 in Year 4
Simpler Template
|  | Discount rate | 0.23
| Year | 0 | 1 | 2 | 3 | 4 | 5
Inflows
| Outflows | Discount rate 0: 50000
| Netflows | -50000 | 15000 | 25000 | 30000 | 20000 | 15000 |  | PV = FV / (1+r)^n | DF = Discount factor
| Discount factor (from Discount factor table) | 1 | 0.83333 | 0.69444 | 0.5787 | 0.48225 | 0.40188 |  | = FV * 1/(1+r)^n
[9 empty] | = FV * DF | Discount rate is sometimes called rate of return.
| PV of netflows | -50000 | 12500 | 17361.1111 | 17361.1111 | 9645.0617 | 6028.1636
| PV of netflows (using formula) | -50000 | 12195.122 | 16524.5555 | 16121.5176 | 8737.9499 | 5328.0182 |  | Discount rate and discount factor are not same thing.
| NPV | Discount rate 0: 8907.1631
| NPV using excel function | Discount rate 0: 8907.1631
Note on B11: Karinda Thomson: =1/(1+C4)^1
Note on B12: Karinda Thomson: =Cost*Disc Factor
Note on B15: Karinda Thomson: Same as above
Note on B16: Karinda Thomson: Same as Costs
Note on B18: Karinda Thomson: Disc benefits - costs
Note on B19: Karinda Thomson: Disc Benefits - previous year Cost (NOT DISC COST)
Note on B22: Karinda Thomson: ROI= (total dsic benefits - total disc costs) / total disc cost

## Question 3
Instruction: Use the provided formula to compute payback
| Payback = Investment / Annual Savings |  |  | ROI = Annual Savings - cost/Investment
| Project A | 3.75 | years | Project A | 0.26667 | 26% | Higher rate of return (gets money back faster compared to Project B)
| Project B | 4 | years | Project B | 0.25 | 25%
Project Alpha has the better payback

## Question 4
Instruction: Use the given table template from the tutorial exercise to answer Question 4
| Project: A |  | Discount factor |  | 0.23 |  | Discount Rate - 0.23 (3% inflation + 20% rate of return)
| Year | Inflows | Outflows | Net Flow | Discount Factor | PV or Discounted Netflow | Discount Factor = 1/(1+discountRate)^year
| 0 |  | -500000 | -500000 | 1 | -500000
| 1 | 50000 |  | 50000 | 0.81301 | 40650.4065
| 2 | 250000 |  | 250000 | 0.66098 | 165245.5549
| 3 | 350000 |  | 350000 | 0.53738 | 188084.3714
[5 empty] | NPV | -106019.6672
|  |  |  | If calculated in EXCEL |  | -106019.6672
Project: B
| Year | Inflows | Outflows | Net Flow | Discount Factor | Discounted CF
| 0 |  | 250000 | -250000 | 1 | -250000
| 1 | 75000 |  | 75000 | 0.81 | 60750
| 2 | 75000 |  | 75000 | 0.66 | 49500
| 3 | 75000 |  | 75000 | 0.54 | 40500
| 4 | 50000 |  | 50000 | 0.44 | 22000
[5 empty] | NPV | -77250
|  |  |  | If calculated in EXCEL |  | -77302.0552
Project: C
| Year | Inflows | Outflows | Net Flow | Discount Factor | Discounted CF
| 0 |  | 75000 |  | 1 | -75000
| 1 | 15000 |  | 15000 | 0.81 | 12150
| 2 | 25000 |  | 25000 | 0.66 | 16500
| 3 | 50000 |  | 50000 | 0.54 | 27000
| 4 | 50000 |  | 50000 | 0.44 | 22000
| 5 | 150000 |  | 150000 | 0.36 | 54000
[5 empty] | NPV | 56650
|  |  |  | If calculated in EXCEL |  | 55713.9304 | Clothing is the only project they should choose (positive NPV)